## Slide 1: Chapter 3
Managing Systems Projects

## Slide 2: Learning Objectives (1 of 2)
After this chapter, you will be able to:
  Illustrate project priorities in the form of a project triangle
  Explain project planning, scheduling, monitoring, and reporting
  Create a work breakdown structure
  Identify task patterns
  Calculate a project’s critical path
  Describe project monitoring and control techniques to keep a project on schedule

## Slide 3: Learning Objectives (2 of 2)
  Explain how project status is reported
  Describe project management software and how it can be of assistance
  Create a risk management plan
  Describe why projects sometimes fail

## Slide 4: Overview of Project Management (1 of 3)
Project management
  Planning, scheduling, monitoring and controlling, and reporting on information system development
What shapes a project?
  Successful projects must be completed on time, within budget, meet requirements, and satisfy users

## Slide 5: Overview of Project Management (2 of 3)
What is a project triangle?
  Challenge: find optimal balance among the factors
    Any change in one leg will affect the other legs
FIGURE 3-2 A typical project triangle includes cost, scope, and time.

## Slide 6: Overview of Project Management (3 of 3)
What does a project manager do?
  Project planning: identifying all project tasks and estimating completion time and costs
  Project scheduling: creating a specific timetable showing tasks, task dependencies, and critical tasks that might delay the project
  Project monitoring: guiding, supervising, and coordinating the project team’s workload
  Project reporting: creating regular progress reports for management, users, and the project team itself

## Slide 7: Creating a Work Breakdown Structure (1 of 8)
Breaking down a project into a series of smaller tasks
  Gantt Chart
    Horizontal bar chart representing a set of tasks
    Shows planned and actual progress on a project
    Simplifies complex projects using a task group

## Slide 8: Creating a Work Breakdown Structure (2 of 8)
PERT/CPM charts
  Program Evaluation Review Technique (PERT)
    Developed by the U.S. Navy
    Utilizes a bottom-up technique
    Useful for scheduling, monitoring, and controlling actual work
    Displays complex task patterns and relationships
  Critical Path Method (CPM)
    Developed by private industry

## Slide 9: Creating a Work Breakdown Structure (3 of 8)
FIGURE 3-4 The top screen shows a Gantt chart with six tasks. The PERT chart in the bottom screen displays an easy-to-follow task pattern for the same project. When the user mouses over the summary box for Task 5, the details become visible.

## Slide 10: Creating a Work Breakdown Structure (4 of 8)
Identifying tasks in a WBS
  Task or activity: any work that has a beginning and end
    Requires the use of company resources such as people, time, or money
    Should be small and manageable
  Projects have events or milestones
    Events or milestones: recognizable reference points used to monitor progress

## Slide 11: Creating a Work Breakdown Structure (5 of 8)
  Listing the tasks
    Tasks might be embedded in a document
  Estimating task duration
    Can be hours, days, or weeks
  Time estimates made by project managers
    Best case-estimate (B), probable-case estimate (P), and worst-case estimate (W)
  After making estimates, the manager assigns a weight to each estimate
    Calculates the task duration

## Slide 12: Creating a Work Breakdown Structure (6 of 8)
FIGURE 3-5 Using a questionnaire requires a series of tasks and events to track the progress. The illustration shows the relationship between the tasks and the events, or milestones, that mark the beginning and end of each task.

## Slide 13: Creating a Work Breakdown Structure (7 of 8)
Factors affecting duration
  Project size
    Identify all project tasks and time required
    Consider time taken for events affecting productivity
  Human resources
    Assemble and guide a development team that has the skill and experience to handle the project
    Deal with factors that could affect the schedule

## Slide 14: Creating a Work Breakdown Structure (8 of 8)
  Experience with similar projects
    Develop time and cost estimates based on the resources used for similar, previously developed information systems
  Constraints
    Define system requirements that can be achieved realistically within the required constraints

## Slide 15: Task Patterns (1 of 6)
Arrangement of tasks in a logical sequence
  Dependent tasks
  Multiple successor tasks
  Multiple predecessor tasks

## Slide 16: Task Patterns (2 of 6)
Using task boxes to create a model
FIGURE 3-10 Each section of the task box contains important information about the task, including the Task Name, Task ID, Task Duration, Start Day/Date, and Finish Day/Date.

## Slide 17: Task Patterns (3 of 6)
Dependent tasks
  Completed in a sequence
    One task can be initiated only after the prior task has been completed
FIGURE 3-12 This example of a dependent task shows that the finish time of Task 1, Day 5, controls the start date of Task 2, which is Day 6.

## Slide 18: Task Patterns (4 of 6)
Multiple successor tasks
  Tasks that can be initiated simultaneously
    Termed concurrent
    Often, two or more concurrent tasks depend on a predecessor task
FIGURE 3-13 This example of multiple successor tasks shows that the finish time for Task 1 determines the start time for both Tasks 2 and 3.

## Slide 19: Task Patterns (5 of 6)
Multiple predecessor tasks
  Initiation of a task depends on completion of two or more prior tasks
FIGURE 3-14 This example of multiple predecessor tasks shows that the start time for a successor task must be the latest (largest) finish time for any of its preceding tasks. In the example shown, Task 1 ends on Day 15, while Task 2 ends on Day 5, so Task 1 controls the start time for Task 3.

## Slide 20: Task Patterns (6 of 6)
Working with complex task patterns
  When several task patterns combine, the facts must be studied very carefully to understand the logic and sequence
    A project schedule will not be accurate if the underlying task pattern is incorrect

## Slide 21: The Critical Path (1 of 3)
Series of tasks which, if delayed, will affect the completion date of the overall project
  If any task on the critical path falls behind schedule, the entire project will be delayed
Calculating the critical path
  Review patterns
  Determine start and finish dates, which will define the critical path

## Slide 22: The Critical Path (2 of 3)
FIGURE 3-18 Example of a PERT/CPM chart with five tasks. Task 2 is a dependent task that has multiple successor tasks. Task 5 has multiple predecessor tasks. In this figure, the analyst has arranged the tasks and entered task names, IDs, and durations.

## Slide 23: The Critical Path (3 of 3)
FIGURE 3-19 Now the analyst has entered the start and finish times, using the rules explained in this section. Notice that the overall project has a duration of 95 days.

## Slide 24: Project Monitoring and Control (1 of 2)
Monitoring and control techniques
  Structured walk-through: review of a project team member’s work by other team members
    Takes place throughout the SDLC
    Known as design, code, or testing reviews based on the phase in which they occur

## Slide 25: Project Monitoring and Control (2 of 2)
Maintaining a schedule
  Projects run into problems or delays
  Projects managers monitor and control work
    Anticipate problems, avoid them, and minimize impact
    Identify potential solutions and select the best way to solve the problem
Tasks and the critical path
  Project managers spend most of their time tracking the tasks along the critical path

## Slide 26: Reporting
Project status meetings
  Project managers schedule regular meetings
    Share updates, discuss common problems, explain new techniques, and help collect data
Project status reports
  Regularly communicated by project managers to supervisors, upper management, or users
Dealing with problems
  Deciding how to handle problems can be difficult

## Slide 27: Project Management Software (1 of 2)
Project managers use software applications to help plan, schedule, monitor, and report on a project
  Most programs offer features such as PERT/CPM, Gantt charts, resource scheduling, project calendars, and cost tracking

## Slide 28: Project Management Software (2 of 2)
Refer to the text for a Microsoft Project task summary example
  Work breakdown structure
  Gantt chart
  Network diagram
  Calendar view

## Slide 29: Risk Management
Steps in risk management
  Develop a risk management plan
  Identify the risks
  Analyze the risks
    Qualitative and quantitative risk analysis
  Create a risk response plan
    Proactive effort to anticipate a risk and describe an action plan to deal with it
  Monitor risks

## Slide 30: Managing for Success
Project management is a challenging task
  Project managers must be alert, technically competent, and highly resourceful
Projects get derailed for a wide variety of reasons
  Business issues
  Budget issues
  Schedule issues

## Slide 31: Summary (1 of 3)
Project management
  Planning, scheduling, monitoring, and reporting on the development of an information system
Project triangle
  Shows three legs that require balancing
    Project cost, scope, and time

## Slide 32: Summary (2 of 3)
Planning, scheduling, monitoring, and reporting
  Take place within a larger development framework
    Creating a work breakdown structure
    Identifying task patterns
    Calculating the critical path
Task patterns establish the sequence of work in a project
  A critical path is a series of tasks that, if delayed, would affect the completion date of the overall project

## Slide 33: Summary (3 of 3)
Gantt chart: horizontal bar chart
  Represents the project schedule with time on the horizontal axis and tasks arranged vertically
PERT/CPM chart: network diagram
  Tasks connected by arrows
Most project managers use powerful software to plan, schedule, and monitor projects
  Microsoft Project